## Gantchart
GANTT CHART TEMPLATE | [6 empty] | Smartsheet Tip ➜ |  |  |  |  | A Gantt chart's visual timeline allows you to see details about each task as well as project dependencies.
PROJECT TITLE : AI BASED SOAR | [6 empty] | INSTUTUTE & DEPARTMENT NAME | [5 empty] | A. P SHAH INSTITUTE OF TECHNOLOGY
PROJECT GUIDE : MR . VISHAL BADGUJAR | [6 empty] | DATE | [5 empty] | 2021-02-16
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION(Weeks) | PCT OF TASK COMPLETE | PHASE ONE | [13 empty] | PHASE TWO | [13 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[7 empty] | WEEK 1 |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception and Initiation
1.1 | Research paper search | Rahul Shruti Aishwarya | 2020-01-08 | 2020-01-26 | 3 | 100% | bar: WEEK 1 F to WEEK 2 T; WEEK 2 F; WEEK 5 M to WEEK 5 F
1.1.1 | Research paper finalization | Rahul , Shruti | 2020-01-10 | 2020-01-27 | 3 | 100% | bar: WEEK 2 W; WEEK 2 F; WEEK 5 M to WEEK 5 F
1.2 | Project Title | Rahul Shruti Aishwarya | 2020-01-10 | 2020-10-01 | 1 | 100% | bar: WEEK 2 W to WEEK 3 W; WEEK 5 M to WEEK 5 F
1.3 | Abstract | Aishwarya | 2020-02-03 | 2020-02-04 | 1 | 100% | bar: WEEK 2 R to WEEK 3 R; WEEK 5 M to WEEK 5 F
1.4 | Objectives | Rahul | 2020-02-08 | 2020-02-16 | 1 | 100% | bar: WEEK 2 F to WEEK 3 R; WEEK 5 M to WEEK 5 F
1.5 | Literature Review | Shruti | 2020-02-08 | 2020-02-16 | 1 | 100% | bar: WEEK 2 F; WEEK 3 T to WEEK 3 R; WEEK 5 M to WEEK 5 F
1.6 | Problem Definition | Rahul Shruti Aishwarya | 2020-02-08 | 2020-02-16 | 1 | 100% | bar: WEEK 2 F; WEEK 3 F; WEEK 5 M to WEEK 5 F
1.7 | Scope | Rahul , Shruti | 2020-02-08 | 2020-02-16 | 1 | 100% | bar: WEEK 2 F; WEEK 3 F; WEEK 5 M to WEEK 5 F
1.8 | Technology stack | Rahul Shruti Aishwarya | 2020-02-08 | 2020-02-16 | 1 | 80% | bar: WEEK 2 F; WEEK 3 F; WEEK 5 M to WEEK 5 F
1.9 | Benefits for environment | Shruti | 2020-02-08 | 2020-02-16 | 1 | 100% | bar: WEEK 2 F; WEEK 3 F; WEEK 5 M to WEEK 5 F
1.1 | Benefits for society | Aishwarya | 2020-02-08 | 2020-02-16 | 1 | 80% | bar: WEEK 2 F; WEEK 3 F; WEEK 5 M to WEEK 5 F
1.11 | Applications | Rahul | 2020-02-08 | 2020-02-16 | 1 | 100% | bar: WEEK 2 F; WEEK 3 F; WEEK 5 M to WEEK 5 F
2 | Project Design
2.1 | Proposed System | Rahul Shruti Aishwarya | 2020-04-15 | 2020-04-27 | 2 | 100% | bar: WEEK 2 F; WEEK 4 M to WEEK 6 F
2.2 | Design(Flow Of Modules) | Rahul | 2020-04-16 | 2020-04-27 | 2 | 100% | bar: WEEK 2 F; WEEK 4 M to WEEK 6 F
2.3 | Activity Diagram | Rahul, Shruti | 2020-04-17 | 2020-04-27 | 2 | 100% | bar: WEEK 2 F; WEEK 4 M to WEEK 6 F
2.4 | Use Case Diagram | Aishwarya | 2020-04-19 | 2020-04-27 | 2 | 100% | bar: WEEK 2 F; WEEK 4 M to WEEK 4 W; WEEK 5 M to WEEK 6 T; WEEK 6 R to WEEK 6 F
2.5 | Description Of Use Case | Shruti , Aishwarya | 2020-04-19 | 2020-04-27 | 2 | 100% | bar: WEEK 2 F; WEEK 4 M to WEEK 6 F
2.6 | Modules | Rahul Shruti Aishwarya | 2020-04-21 | 2020-04-27 | 2 | 100% | bar: WEEK 1 M to WEEK 6 F
2.6.1 | Module-1 | Rahul | 2020-04-21 | 2020-04-27 | 2 | 100% | bar: WEEK 2 F; WEEK 4 T to WEEK 5 F; WEEK 6 W to WEEK 6 F
2.6.2 | Module-2 | Shruti | 2020-04-23 | 2020-04-27 | 2 | 100% | bar: WEEK 2 F; WEEK 4 M to WEEK 4 W; WEEK 5 M to WEEK 6 F
2.6.3 | Module-3 | Aishwarya | 2020-04-24 | 2020-04-27 | 2 | 100% | bar: WEEK 2 F; WEEK 4 M to WEEK 5 M; WEEK 5 W to WEEK 6 F
2.6.4 | Module-4 | Rahul | 2020-04-25 | 2020-04-27 | 2 | 100% | bar: WEEK 2 F; WEEK 4 M to WEEK 4 W; WEEK 5 M to WEEK 5 R; WEEK 6 M to WEEK 6 F
2.7 | Preparation Of Report | Rahul Shruti Aishwarya | 2020-04-26 | 2020-04-27 | 2 | 100% | bar: WEEK 2 F; WEEK 4 M; WEEK 4 W to WEEK 6 W; WEEK 6 F
3 | Project Implementation |  |  |  |  | 100%
3.1 | Collection of large volumes of data : Alerts | Rahul | 2021-01-21 | 2021-03-15 | 4 | 100% | bar: WEEK 2 F; WEEK 5 M to WEEK 6 W
3.2 | Creating of Docker Components | Rahul | 2021-01-21 | 2021-03-15 | 4 | 30% | bar: WEEK 2 F; WEEK 5 M to WEEK 6 F
3.3 | Generation of playbooks using Ansible | Shruti | 2021-01-21 | 2021-03-15 | 4 | 30% | bar: WEEK 2 F; WEEK 5 M to WEEK 6 F
3.4 | Admin Dashboard using Cockpit | Aishwarya | 1-21-21 | 3-15-21 | 4 | 80% | bar: WEEK 2 F; WEEK 4 M to WEEK 6 R; WEEK 7 F; WEEK 10 F
3.5 | Automated STIX Engine | Rahul | 1-21-21 | 3-15-21 | 4 | 100% | bar: WEEK 2 F; WEEK 4 M to WEEK 6 F
3.4 | Result Generation and Categorization | Rahul Shruti Aishwarya | 2021-01-21 | 2021-03-15 | 4 | 85-95% | bar: WEEK 2 F; WEEK 4 M to WEEK 6 F
4 | Testing
4.1 | Design of Test Cases | Rahul Shruti Aishwarya | 2021-01-21 | 2021-02-02 | 4 | 75% | bar: WEEK 1 R to WEEK 1 F; WEEK 4 M to WEEK 6 W; WEEK 7 W to WEEK 7 F; WEEK 10 W to WEEK 10 F
4.3 | Prototyping | Shruti Aishwarya | 2020-10-15 | 2020-11-01 | 2 | 90% | bar: WEEK 1 T to WEEK 1 F; WEEK 4 M to WEEK 6 R; WEEK 7 T to WEEK 7 F; WEEK 10 T to WEEK 10 F
4.4 | Development | Rahul | 2021-03-01 | 2021-04-15 | 4 | 80% | bar: WEEK 1 T to WEEK 1 F; WEEK 4 M to WEEK 6 F; WEEK 7 W to WEEK 7 F; WEEK 10 W to WEEK 10 F
4.5 | Collection of large volumes of data i.e Alerts | Rahul | 2021-01-15 | 2021-02-11 | 4 | 100% | bar: WEEK 1 T to WEEK 1 F; WEEK 4 M to WEEK 6 F; WEEK 7 W to WEEK 7 F; WEEK 10 W to WEEK 10 F
4.6 | Generateappropriate responses using playbooks | Shruti | 2021-02-10 | 2021-03-15 | 3 | 25% | bar: WEEK 1 T to WEEK 1 F; WEEK 4 M to WEEK 6 F; WEEK 7 W to WEEK 7 F; WEEK 10 W to WEEK 10 F
4.7 | Validation and Analysis using Ti | Aishwarya | 2021-03-01 | 2021-03-12 | 2 | 100% | bar: WEEK 1 T to WEEK 1 F; WEEK 4 M to WEEK 6 F; WEEK 7 W to WEEK 7 F; WEEK 10 W to WEEK 10 F
4.8 | Automated STIX Engine | Rahul | 2021-03-10 | 2021-03-20 | 2 | 100% | bar: WEEK 1 T to WEEK 1 F; WEEK 4 M to WEEK 6 F; WEEK 7 W to WEEK 7 F; WEEK 10 W to WEEK 10 F
4.9 | Result Generation and Categorization | Rahul Shruti Aishwarya | 2021-03-21 | 2021-03-28 | 1 | 95% | bar: WEEK 1 F to WEEK 3 F; WEEK 4 W to WEEK 6 F
5 | Result and Analysis | bar: WEEK 1 M; WEEK 2 F; WEEK 4 W to WEEK 12 F
5.1 | Graphical Representation | Shruti Aishwarya | 2021-04-08 | 2021-05-01 | 1 | 100% | bar: WEEK 2 F; WEEK 4 W to WEEK 6 F
5.2 | Report Presentation | Rahul Shruti Aishwarya | 2021-04-15 | 2021-05-10 | 1 | 100% | bar: WEEK 2 F; WEEK 4 W to WEEK 5 F; WEEK 6 T to WEEK 6 F